## excel
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 33.5 | 21.5 | 31
Planned Time | 0.24306 |  | 1899-12-31 02:26
Actual Tiempo |  | 0.20903 | 1899-12-31 00:41
CPI (Cost-Performance Index) |  |  | 1.07
% Reuse | 0% | 0% | 8.17%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 4.57 | 0 | 3.92
Total Defects/KLOC or equivalent | 4.57 | 0 | 3.92
Yield % | 0% | 0 | 0%
Code Review Rate | 590 | 324 | 528
% Appraisal COQ | 10.3% | 13.3% | 10.9%
% Failure COQ | 9.15% | 8.64% | 9.05%
COQ A/F Ratio | 1.13 | 1.54 | 1.21
PQI | 0.08 | 0.16 | 0.09
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 05:19 PM el 1/05/2017