## excel (12)
/Non Project/PSP Fundamentals & Advanced/Program 4
PSP2 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 180 | 180 | 432
Deleted (D) | 50 | 47 | 166
Modified (M) | 15 | 26 | 122
Added (A) | 96.8 | 60 | 357
Reused (R) | 20 | 0 | 4
Added and Modified (A+M) | 112 | 86 | 479
Total Size (T) | 247 | 193 | 627
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 123 | 147 | 530
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:18 PM el 19/03/2017