## excel (11)
/Non Project/PSP Fundamentals & Advanced/Program 2
Size Estimating Template (instructions...)
The PROBE Wizard uses Estimated Proxy Size as the basis for generating final estimates for size and time. However, after you last ran the PROBE Wizard, you modified the estimates on this form, causing the Estimated Proxy Size to change. Your current PROBE estimates are based upon the old value of Estimated Proxy Size. To resolve this problem, you should double-check the values in the form below, then run the PROBE Wizard again.
Project Owner | AndrÃ©s Felipe Mape
Size Measure | LOC
BASE PARTS |  |  | Estimated |  |  |  |  | Actual
|  |  | BASE | DELETED | MODIFIED | ADDED |  | BASE | DELETED | MODIFIED | ADDED
Programa1 |  |  | 131 | 50 | 40 | 30 |  | 131 | 60 | 53 | 46
add more rows for base parts... | Total: |  | 131 | 50 | 40 | 30 |  | 131 | 60 | 53 | 46
PARTS ADDITIONS |  |  | Estimated | [5 empty] | Actual
|  |  | TYPE | ITEMS | REL. SIZE | SIZE | NR |  | SIZE | ITEMS | NR
Clase para almacenar la informacion del archivo |  |  | Data | 1 | Small | 4.8 |  |  | 15 | 2
Evaluar expresiones regulares |  |  | Calculation | 1 | Small | 5.1 |  |  | 29 | 3
add more rows for parts additions... |  |  |  | Total: |  | 9.9 |  |  | 44
REUSED PARTS |  |  | Estimated |  | Actual
|  |  | SIZE |  | SIZE
Main |  |  | 5 |  | 4
add more rows for reused parts... | Total: |  | 5 |  | 4
TOTAL SIZE |  | Actual
SIZE
Actual Size of Finished Product: |  | 117
Instructions: During the planning phase, complete the "Estimated" columns in the form above, then use the PROBE Wizard to fill out the fields below.
|  |  | SIZE |  | TIME
Added Size (A): | A = BA + PA |  | 39.9
Estimated Proxy Size (E): | E = BA + PA + M |  | 79.9
Last Estimated Proxy Size: (The value used on the last run of the PROBE Wizard) |  |  | 79.9
PROBE estimating basis used: (A, B, C, or D) |  |  | D |  | D
Correlation: (r2) |  |  | N/A |  | N/A
Regression Parameters: | B0 (size and time) |  | 0 |  | N/A
Regression Parameters: | B1 (size and time) |  | 1 |  | N/A
Projected Added and Modified Size (P): | P = B0size + B1size * E |  | 79.9
Estimated Total Size (T): | T = P + B - D - M + R |  | 126
Estimated Total New Reusable (NR): | (sum of NR items) |  | 0
Estimated Total Development Time: | Time = B0time + B1time * E |  |  |  | 0.10417
Prediction Range: | Range |  | N/A |  | N/A
Upper Prediction Interval: | UPI = P + Range |  | N/A |  | N/A
Lower Prediction Interval: | LPI = P - Range |  | N/A |  | N/A
Prediction Interval Percent: |  |  | N/A |  | N/A
View PROBE Report
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.