## excel
/Non Project/PSP Fundamentals & Advanced/Program 3
PSP2 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 38.8 | 27.9 | 37.7
Planned Time | 0.22431 |  | 0.43264
Actual Tiempo |  | 0.22847 | 0.41875
CPI (Cost-Performance Index) |  |  | 1.03
% Reuse | 0% | 0% | 0.95%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 13.3 | 0 | 7.92
Total Defects/KLOC or equivalent | 13.3 | 0 | 7.92
Yield % | 0% | #DIV/0! | 0%
Code Review Rate | 418 | 340 | 842
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 04:14 PM el 4/03/2017